## Estimates
Business Object/Area:
|  |  |  | System (direction) | Cost
# | Functional Point | Description | Category | Design Point | Rollout Phase | Design | Develop | Deploy | Total hours | Resource | Cost
F-001a | Backend Development | - Social Media APIs Integration (Social, Google, News, etc.) | MileStone 1 Feature | Development & Design | Phase 1 | 14 | 46 | 0 | 60 | Senior consultant/ Solution Developer - 0001 | 350
F-001b | Backend Development | - Database Setup (PostgreSQL, Elasticsearch) | MileStone 1 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-001c | Backend Development | - Data Processing Pipelines (Real-time Ingestion) | MileStone 1 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-001d | Backend Development | - Web Scraping (for platforms without APIs) | MileStone 2 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 300
F-001e | Backend Development | - Search & Maps Data (Google Maps, Reviews, Geo-tagging) | MileStone 2 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-002a | Data Collection | - Data Cleaning, Deduplication, Normalization | MileStone 2 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-003a | NLP Model Implementation (Sentiment & Emotion Analysis) | - Multi-language Support (English & Arabic) | MileStone 3 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 500
F-003b | NLP Model Implementation (Sentiment & Emotion Analysis) | - Emotion Classification (Joy, Anger, Sadness, etc.) | MileStone 3 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-003c | NLP Model Implementation (Sentiment & Emotion Analysis) | - Custom Sentiment Models (Handling slang & cultural nuances) | MileStone 3 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-003d | NLP Model Implementation (Sentiment & Emotion Analysis) | - Entity-Level & Aspect-Based Sentiment Analysis | MileStone 3 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-003e | NLP Model Implementation (Sentiment & Emotion Analysis) | - Common Keywords & Phrase Extraction | MileStone 3 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-003f | NLP Model Implementation (Sentiment & Emotion Analysis) | - Customer Persona Detection & Profiling | MileStone 3 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-004a | Social Listening & Monitoring | - Real-Time Alerts for sentiment changes | MileStone 4 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 10
F-004b | Social Listening & Monitoring | - Tracking Hashtags, Keywords & Competitors | MileStone 4 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-004c | Social Listening & Monitoring | - Conversation Thread Tracking | MileStone 4 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-005a | Frontend Development | - React.js/Vue.js Dashboard | MileStone 5 Feature | Development & Design | Phase 1 | 14 | 50 | 0 | 64 | Senior consultant/ Solution Developer - 0001 | 10
F-005b | Frontend Development | - Data Visualization (Chart.js, D3.js) | MileStone 5 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-005c | Frontend Development | - Responsive & RTL Arabic Support | MileStone 5 Feature | Development & Design | Phase 1 | 14 | 50 | 0 | 64 | Senior consultant/ Solution Developer - 0001
F-006a | Dashboard & Reporting | - Customizable KPIs and Widgets | MileStone 6 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 50
F-006b | Dashboard & Reporting | - Sentiment Overview (Loved, Neutral, Hated) | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006c | Dashboard & Reporting | - Geo Insights (Sentiment by region) | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006d | Dashboard & Reporting | - Top Posts and Mentions | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006e | Dashboard & Reporting | - User Activity Levels (Engagement per platform) | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006f | Dashboard & Reporting | - Competitor Benchmarking | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006g | Dashboard & Reporting | - Engagement Trends Analysis (Daily, Weekly, Monthly) | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 8 | 28 | Senior consultant/ Solution Developer - 0001
F-006h | Dashboard & Reporting | - Word Cloud & Keyword Analysis | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006i | Dashboard & Reporting | - Persona Insights Analysis | MileStone 6 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-006j | Dashboard & Reporting | - Exportable Reports (PDF, Excel) | MileStone 6 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-007a | User Management | - Role-Based Access Control | MileStone 7 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 10
F-007b | User Management | - Multi-User Support (Enterprise onboarding) | MileStone 7 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-008a | Security & Compliance | - Authentication (OAuth 2.0, Secure Login) | MileStone 8 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 50
F-008b | Security & Compliance | - Data Protection (Encryption, GDPR) | MileStone 8 Feature | Development & Design | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-008c | Security & Compliance | - Local Compliance (Saudi Regulations) | MileStone 8 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-008d | Scalability & Performance | - High Availability (Reliable Data Processing) | MileStone 9 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001 | 100
F-008e | Scalability & Performance | - Real-Time Data Processing Pipelines | MileStone 9 Feature | Development & Design | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-009a | Testing & Quality Assurance | - Unit & Integration Testing | MileStone 10 Feature | Testing | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 100
F-009b | Testing & Quality Assurance | - Performance & Security Testing | MileStone 10 Feature | Testing | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-0010a | Deployment & Infrastructure | - Cloud Hosting (AWS/GCP/Azure) | MileStone 11 Feature | Rollout | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001 | 50
F-0010b | Deployment & Infrastructure | - CI/CD Pipelines (Continuous Deployment) | MileStone 11 Feature | Rollout | Phase 1 | 10 | 30 | 0 | 40 | Senior consultant/ Solution Developer - 0001
F-0010c | Deployment & Infrastructure | - Monitoring & Logging for System Health | MileStone 11 Feature | Rollout | Phase 1 | 4 | 16 | 0 | 20 | Senior consultant/ Solution Developer - 0001
F-0011a | Project Management & Support | - Agile Development Process throughtout project lifecycle | MileStone 1 Feature | Support | Phase 1 | 0 |  | 40 | 40 | Senior consultant/ Solution Developer - 0001 | 100
Sheet Summary
Phase Totals |  | Hours | Cost($)
| Phase 1 Total | 1436 | 1630
| Phase 2 Total | 0 | 0
Resource totals |  | Phase 1 | Phase 2
|  | 2 | 0